## Big Masses
Project Big Masses
1 | Players List
2 | Classes
3 | Identity
4 | Seeding Admins, Players, and Fans.
5 | News/Events
6 | Private Messages
7 | Forum & Comments.
8 | Fixing the home page.
9 | Fixing all the other views accordingly.
10 | Distributing Authorization per role.
11 | Finalization

## Details Check List
Task No. | WEEK | Done | Role | Sub-Tasks | Big Mass
1 | 1 |  | RAFI | Designing the Models as per the Application needs. | Classes
2 | 1 |  | RAFI | Creating three roles (Admin, Player, Fans) | Identity
3 | 1 |  | RAFI | Creating Users in the Seed method two admins | Seeding SQL
4 | 1 |  | RAFI | Creating Users in the Seed method 22 players
5 | 1 |  | RAMI | Displaying the list of players in a view | Players List
6 | 1 |  | RAMI | Programming Edit player from Players List using AJAX from Details view
Programming Add player to Players List
7 | 1 |  | RAMI | In additon the admin can delete fans
8 | 1 |  | RAMI | Programming Details as a new page
9 | 2 |  | RAMI | View all the messages of the player (sent/received) | Private Messages
10 | 2 |  | RAFI | Write new message and send it
11 | 2 |  | RAFI | Give a notification to the player when received a new message
12 | 2 |  | FIRAS | Player can sort messages as (sent/received)
13 | 2 |  | RAFI | Replying to a message will be like creating a new one
14 | 2 |  | RAFI | Player can delete any sent or received message from his list but not from the data base
15 | 2 |  | RAMI | Displaying all the posts on the index page of forum | Forum & Comments.
16 | 2 |  | FIRAS | Players and admins only can write new posts
17 | 2 |  | FIRAS | everyone registerd on the application can write a comment (admin,player,fan) - AJAX
18 | 2 |  | FIRAS | Only Admins are allowed to delete a post or comment
19 | 1 |  | FIRAS | Programming the news page | New/Events
20 | 1 |  | FIRAS | Only Admins are allowed to add/delete/edit News/Events
21 | 2 |  | FIRAS | Styling the News/Events pags
22 | 3 |  | FIRAS | Styling the home page | Fixing the home page.
23 | 3 |  | RAMI | Styling the Players view | Fixing all the other views accordingly.
24 | 3 |  | RAMI | Styling the messages view
25 | 3 |  | RAMI | Styling the Forum and the comments Views
26 | 3 |  | RAFI | Finally Distributing authorities depending on above | Distributing Authorization per role.
27 | 4 |  | RAFI | Finalizing the project for set up | Finalization

## Time Planing
Sprint |  | Role | Tasks | Sub-Tasks
W1 | d1 | RAFI | Planning the Project
W1 | d1 | RAFI | Creating Project MVC web application.
W1 | d1 | RAFI | Creating Classes and models.
W1 | d1 | RAFI | Data base creation.
W1 | d1 | RAMI | Identity
W1 | d1 | RAMI | Creating three roles: | Admin
W1 | d1 | RAMI | Creating three roles: | Player
W1 | d1 | RAMI | Creating three roles: | Fan
W1 | d2 | RAMI | Seeding the data base with: | Two admins.
W1 | d2 | FIRAS | Seeding the data base with: | 22 Players
W1 | d2 | RAMI | Setting roles for each player and admin
W1 |  | FIRAS | Ditributing Authorizations.
W1 | d3 | FIRAS | Programming the News/Events.
W1 |  | FIRAS | Disigning the views:
W1 |  | FIRAS | Disigning the views: | _Layout.
W1 |  | FIRAS | Disigning the views: | Home.
W1 |  | FIRAS | Disigning the views: | About.
W1 |  | RAFI | Disigning the views: | Contact.
W1 |  | FIRAS | Disigning the views: | News/Events.
W2 |  | RAMI | Disigning the views: | Members (Players).
W2 |  | RAMI | Disigning the views: | Add/Edit/Remove
W2 |  | RAMI | Disigning the views: | Messages.
W2 |  | RAMI | Disigning the views: | Posts.
W2 |  | RAMI | Disigning the views: | Comments.
W2 |  | RAMI | Programming the Forum.
Programming the Comments on the posts
W2 |  | RAMI | Programming the messages.
W3
W3
W3